## Sheet1
Architect of the Capitol OIG Overdue Recommendations as of April 7, 2024
Project Name | Project Code | Group | Report Issuance Date | Unallowed/Disallowed Cost | Funds Put to Better Use | Questioned Costs | Released for Follow Up | Recommendation Title | Response to Recommendation | Recommendation | Recommendation State | Due Date | Days Till Due | Revised Due Date (Extension) | Actual Closed Date | Responsible Office | Resolution Status | Management's Response | Management's Final Action | Responsible Division/Jurisdiction | Releasable? | Significant?
Evaluation of AOC's Compliance with It's Discipline Order | 2019-0001-IE-P | Inspection and Evaluation Division | 2020-06-05 | 0 | 0 | 0 | Yes | Recommendation C | Concur | We recommend that the AOC develop and publish a discipline policy for exempt personnel, for transparency and consistency with other employee groups. | Not Started | 2021-06-05 | -1037 | 2024-10-01 |  | Office of the Chief Administrative Officer | Open - Resolved | The AOC concurs with the OIG recommendation to develop and publish a discipline policy for Senior Rated (SR) personnel, for transparency and consistency with other employee groups. |  | Human Capital Management Division | Yes | No
Architect of the Capitol's (AOC)'s Role in Securing the Capitol Campus During Large Public Gatherings | 2021-AUD-005-O | cccccbclkcluvcgjuiccbfcfldljlndiikhvbidvvhnj | 2021-05-05 | 0 | 0 | 0 | Yes | Recommendation 2 | Concur | We recommend the AOC Office of the Chief Security Officer coordinate with U.S. Capitol Police to draft a memorandum of agreement to support the roles and responsibilities and services required for preparation and execution of the perimeter security plans for large public events. | In Progress | 2022-05-05 | -703 |  |  | Office of the Chief Security Officer, Architect of the Capitol | Open - Resolved | Memoranda of Agreement between the USCP and the AOC's Chief Security Officer are on hold pending ongoing working groups tasked with developing standard procedures for events and incidents. In the interim, the Board implemented a process that requires the USCP to coordinate with the AOC's Office of the Chief Security Officer (OCSO) during planning. The official requests for support come from the USCP Assistant Chief level to the Chief Security Officer. The AOC's Chief Security Officer provides the details on the deployment/redeployment timelines to the Board Deputies prior to execution. | See supporting documentation. |  | Yes | No
Architect of the Capitol's (AOC)'s Role in Securing the Capitol Campus During Large Public Gatherings | 2021-AUD-005-O | Audit Division | 2021-05-05 | 0 | 0 | 0 | Yes | Recommendation 3 | Concur | We recommend the AOC Office of the Chief Security Officer establish well-defined policies and procedures with a preparation checklist for jurisdictions based on the severity of threat that provides clear guidance on execution of support activities related to coordination, mobilization, de-mobilization, asset protection and reporting of activities associated with special events across the Capitol campus. | In Progress | 2022-05-05 | -703 |  |  | Office of the Chief Security Officer, Architect of the Capitol | Open - Resolved | The OCSO is participating in working groups led by the USCP to develop standards and procedures based on event type and threats. Once the Board approves the standards and procedures, the AOC will develop AOC-specific policies to implement the required measures. In the interim, OCSO will continue to publish "Red Notices" prior to significant events detailing requirements. Reporting will be accomplished through WebEOC for non-sensitive items. | See supporting documentation. |  | Yes | No
Architect of the Capitol's (AOC)'s Role in Securing the Capitol Campus During Large Public Gatherings | 2021-AUD-005-O | Audit Division | 2021-05-05 | 0 | 0 | 0 | Yes | Recommendation 4 | Concur | We recommend the AOC coordinate with the U.S. Capitol Police Board and legislative stakeholders to evaluate the overall focus on campus security, and reevaluate the responsibilities for design, installation and maintenance of the Capitol campus security systems and determine who should execute those responsibilities. | In Progress | 2022-05-05 | -703 |  |  | Office of the Chief Security Officer, Architect of the Capitol | Open - Resolved | The AOC is actively and continuously working with the USCP and congressional stakeholders to clarify responsibilities for the design, installation and maintenance of physical security measures on the Capitol campus. | See supporting documentation. |  | Yes | No
Architect of the Capitol's (AOC)'s Role in Securing the Capitol Campus During Large Public Gatherings | 2021-AUD-005-O | Audit Division | 2021-05-05 | 0 | 0 | 0 | Yes | Recommendation 5 | Concur | We recommend the AOC Office of the Chief Security Officer hold a security briefing with AOC senior leadership for each event, which highlights the security threats and risks identified during their monitoring and received from coordinating agencies along with AOC’s approach to manage such risks and instructions for jurisdictions to execute the developed preparation checklist. | In Progress | 2022-05-05 | -703 |  |  | Office of the Chief Security Officer, Architect of the Capitol | Open - Resolved | OCSO provided briefings and updates to the AOC's senior leadership on significant events prior to the events of January 6, 2021, and will continue to do so. | See supporting documentation. |  | Yes | No
Architect of the Capitol's (AOC)'s Role in Securing the Capitol Campus During Large Public Gatherings | 2021-AUD-005-O | Audit Division | 2021-05-05 | 0 | 0 | 0 | Yes | Recommendation 6 | Concur | We recommend the AOC inform the U.S. Capitol Police of the deferred security maintenance work elements prior to large public gatherings and events on the Capital campus. | In Progress | 2022-05-05 | -703 |  |  | Office of the Chief Security Officer, Architect of the Capitol | Open - Resolved | The AOC currently informs and will continue to inform the USCP of any impaired or non-functioning security elements as soon as they are identified. | See supporting documentation. |  | Yes | No
FY21 Audit_Undelivered Orders OIG-AUD-2021-06 | 2021-AUD-004-A | Audit Division | 2021-09-29 | 0 | 479907.61 | 90109.58 | Yes | Recommendation 1 | Concur | We recommend that the Architect of the Capitol (AOC) review and properly closeout the following dormant unliquidated obligations (ULOs):• 68 invalid ULOs valued at $479,907.61;• Nine unsupported questioned ULOs valued at $90,109.58;• Nine valid ULOs valued at $8,230 that have not received a final invoice; and• 231 ULOs with balances less than $50.Funds put to better use: $479,907.61 and Questioned costs: $90,109.58 | Reviewed-In Progress | 2022-09-29 | -556 | 2024-05-31 |  | Office of the Chief Financial Officer, Architect of the Capitol | Open - Resolved | Concur. The AOC concurs with the report recommendation and will take action to implement such recommendation. |  | Accounting Division | Yes | No
FY21 Audit_Undelivered Orders OIG-AUD-2021-06 | 2021-AUD-004-A | Audit Division | 2021-09-29 | 0 | 479907.61 | 90109.58 | Yes | Recommendation 2 | Concur | We recommend that the Architect of the Capitol (AOC) ensure supporting documentation for unliquidated obligations is maintained and readily available. | Reviewed-In Progress | 2022-09-29 | -556 | 2024-05-31 |  | Office of the Chief Financial Officer, Architect of the Capitol | Open - Resolved | Concur. The AOC concurs with the report recommendation and will take action to implement such recommendation. |  | Accounting Division | Yes | No
FY21 Audit_Undelivered Orders OIG-AUD-2021-06 | 2021-AUD-004-A | Audit Division | 2021-09-29 | 0 | 479907.61 | 90109.58 | Yes | Recommendation 3 | Concur | We recommend that the Architect of the Capitol (AOC):• Finalize the new Quarterly Financial Review (QFR) SharePoint application and ensure this new application addresses the current and prior year audit findings; and• Revise the AOC’s policies and procedures to align with the new application. | Reviewed-In Progress | 2022-09-29 | -556 | 2024-05-31 |  | Office of the Chief Financial Officer | Open - Resolved | Concur. The AOC concurs with the report recommendation and will take action to implement such recommendation. | OCFO finalized the Quarterly Financial Review (QFR) SharePoint application and revised policies and procedures to align with the new application. Specifically, AOC Order 32-10 (revised October 8, 2021) defines the Quarterly Financial Review Application (QFR Application) as a SharePoint application developed to facilitate the AOC’s QFR process. The QFR Application notifies individuals responsible for open commitments and ULOs when the age of the items exceeds established timelines without appropriate action. The application also enables electronic notification and routing of justifications and requests for modification. Fund Managers, or their designees, will also provide their required certification of open commitments and obligations within the application. In addition, user manuals are available online within the application (see pg. 7 of 10). The OIG recommendation also included language that AOC "ensure this new application addresses the current and prior year audit findings." Both the application and the revised policy meet the intent of the recommendation; however, the AOC did not provide results from their own testing or proof that the open obligations identified by the OIG (in the audit report) have been resolved. Until the AOC provides that documentation, the OIG can say definitively that current and prior year audit findings have been addressed. | Accounting Division | Yes | No
Evaluation of AOC's Fleet Management Program | 2021-0001-IE-P | Inspection and Evaluation Division | 2021-11-29 | 0 | 0 | 0 | Yes | Recommendation 2 | Concur | We recommend the Chief Administrative Officer review jurisdiction-level fleet policies and standardize jurisdictional best practices across the Architect of the Capitol (AOC), where appropriate. | Not Started | 2022-11-29 | -495 | 2024-10-01 |  | Office of the Chief Administrative Officer | Open - Resolved | The AOC concurs with the auditor's recommendation. As part of the working group, team members will review jurisdiction-level policies and implement corrective actions as necessary to fill gaps in fleet policies and procedures to standardize best practices across the AOC.The estimated completion date for Recommendation 2 is June 30, 2022. | AOC requested extension to date for response to this recommendation of 30 days after the onboarding of a new Chief Administrative Officer. Date TBD. | Supplies, Services & Material Management Division | Yes | No
Evaluation of AOC's Fleet Management Program | 2021-0001-IE-P | Inspection and Evaluation Division | 2021-11-29 | 0 | 0 | 0 | Yes | Recommendation 3 | Concur | We recommend the Chief Administrative Officer procure an Architect of the Capitol (AOC)-wide fleet management information system with best-in-class fleet management capabilities, to include vehicle inventory, acquisition, disposal, utilization, cost, mileage, and fuel use information for each vehicle, and automatic notification to fleet managers of maintenance due. | Not Started | 2022-11-29 | -495 | 2024-10-01 |  | Office of the Chief Administrative Officer | Open - Resolved | The AOC concurs with the auditor's recommendation. SSMMD will conduct market research to evaluate the availability of a best-in-class fleet management database that captures comprehensive vehicle information to include acquisition, inventory, use costs such as mileage and fuel, and disposal information. Please note that any recommendation requiring additional appropriated funds, FTEs or other resources will need to be requested in future budget submissions.An acquisition plan and identification of resources required for Recommendation 3 will be available by June 30, 2022. |  | Supplies, Services & Material Management Division | Yes | No
Evaluation of AOC's Fleet Management Program | 2021-0001-IE-P | Inspection and Evaluation Division | 2021-11-29 | 0 | 0 | 0 | Yes | Recommendation 5 | Concur | We recommend the Chief Administrative Officer, in coordination with Architect of the Capitol (AOC) organization leaders, review and revise AOC-wide and jurisdictional policies to include standards for vehicle utilization, and guidance for implementing these standards while maintaining jurisdiction-level operational flexibility. | Not Started | 2022-11-29 | -495 | 2024-10-01 |  | Office of the Chief Administrative Officer | Open - Resolved | The AOC concurs with the auditor's recommendation. As part of the working group, SSMMD will meet with jurisdictional and organization leaders to gather input and recommendations on fleet use and will revise Order 34-2 and jurisdictional policies as appropriate.A program plan addressing Recommendation 5 including resources requests will be available by June 30, 2022. |  | Supplies, Services & Material Management Division | Yes | No
Evaluation of AOC Security Badging Process | 2022-0001-IE-P | Inspection and Evaluation Division | 2022-07-25 | 0 | 0 | 0 | Yes | Recommendation 1 | Concur | We recommend the Office of the Chief Security Officer develop and implement a suitability policy for AOC employees and consolidate and implement revisions, as appropriate, to the current contractor suitability policy. Additionally, develop and implement a standardized timeline for policy revision and update within the current Fiscal Year. | In Progress | 2023-07-25 | -257 | 2024-10-01 |  | Office of the Chief Security Officer | Open - Resolved | The AOC concurs. The Office of the Chief Security Officer (OCSO) staff have completed coordination of the draft AOC Order 42-6, Staff Personnel Suitability Program Policy, with the Human Capital Management Division and are finalizing the associated forms. The draft order will enter the AOC's publication process no later than July 15, 2022. The OCSO has also drafted AOC Order 42-7, Contractor Suitability Policy, which will replace Order 731-1, Contractor Suitability Policy. The draft of AOC Order 42-7 will be entered into the AOC's publication process no later than September 1, 2022, after resolution of outstanding comments. The OCSO will conduct annual reviews of both orders no later than March 31st of each year. |  |  | Yes | No
Evaluation of AOC Security Badging Process | 2022-0001-IE-P | Inspection and Evaluation Division | 2022-07-25 | 0 | 0 | 0 | Yes | Recommendation 3 | Concur | We recommend that the Office of the Chief Security Officer develop and implement suitability policy language to include clear lines of responsibility and processes. Improvements should include:• In the contractor suitability policy, assign the responsibility for the centralized recordkeeping of intra-agency badging agreement Memorandums of Understanding or Agreements to the OCSO; and• In both policies, guidance and requirements for secure badge return and protection and oversight of Personally Identifiable Information. | Not Started | 2023-07-25 | -257 | 2024-10-01 |  | Office of the Chief Security Officer | Open - Resolved | The AOC concurs and will include responsibilities in the draft AOC Order 42- 7, Contractor Personnel Suitability Program Policy. This order applies to all persons who have access to AOC controlled grounds, facilities and information systems and includes AOC contractors, subcontractors and the employees of such contractors and subcontractors. The order will assign the responsibility for the centralized recordkeeping of intra-agency badging agreement Memorandums of Understanding or Agreements to the OCSO and requirements for secure badge return and protection and oversight of Personally Identifiable Information. |  |  | Yes | No
Evaluation of ITD Inventory Accountability and Controls | 2022-0002-IE-P | Inspection and Evaluation Division | 2022-07-28 | 0 | 0 | 0 | Yes | Recommendation 1 | Concur | We recommend that the Chief Information Officer update Information Technology Division’s current policy for accountable Information Technology property, to include the incorporation of defined program personnel roles, requirements aligned with the property management lifecycle, and all current program procedures. | Not Started | 2022-07-28 | -619 | 2024-03-31 |  | Office of the Chief Administrative Officer | Open - Resolved | The AOC concurs. The Information Technology Division will update AOC Order 8-4, Accountable Information Technology Property to incorporate defined program personnel roles and align requirements with the property management life cycle and all current program procedures.The estimated completion date for Recommendation 1 is June 30, 2023. |  | Information Technology Division | Yes | No
Evaluation of ITD Inventory Accountability and Controls | 2022-0002-IE-P | Inspection and Evaluation Division | 2022-07-28 | 0 | 15385.39 | 0 | Yes | Recommendation 2 | Concur | We recommend that the Chief Information Officer continue pursuit of transitioning to a single asset management system that addresses its program needs to track accountable and consumable Information Technology (IT) property and establish a detailed implementation plan with target dates to transition to a single asset management system for accountable and consumable IT property as currently captured in Cireson and Jumpstock. | Not Started | 2022-07-28 | -619 |  |  | Office of the Chief Administrative Officer | Open - Resolved | The AOC concurs. Leveraging a robust IT service management (ITSM) platform with incorporated IT asset management, when properly implemented, provides significant2022-0002-IE-P 13accountability and life cycle of IT assets in alignment with industry and Information Technology Infrastructure Library best practices. ITD is currently assessing more robust ITSM tools for future implementation.The estimated completion date for Recommendation 2 is September 30, 2024. This is an unfunded requirement requiring adherence to the AOC budget and procurement processes. | 8/11/2023- ITD has requested funding to support the acquisition of and transition to a more robust IT servicemanagement and asset management system. ITD has initiated an internal assessment project tovalidate the feasibility of and develop an implementation plan for consolidating the agency'snon-accountable or consumable IT inventory currently in Jumpstock into the existingaccountable IT property asset management system (Cireson), The feasibility assessment andimplementation plan development are expected to be completed in quarter four of Fiscal Year2023 and will include a target date for inventory consolidation within a single asset managementsystem with a more narrowly focused asset management solution that may be a lower cost andmore effective for the agency. | Information Technology Division | Yes | No
Evaluation of ITD Inventory Accountability and Controls | 2022-0002-IE-P | Inspection and Evaluation Division | 2022-07-28 | 0 | 0 | 0 | Yes | Recommendation 3 | Concur | We recommend that the Architect of the Capitol (AOC) revise the Board of Survey Process with codified punitive actions to act as a deterrent against future instances ofegregious employee negligence and misconduct regarding the loss of AOC property, including both Information Technology mobile devices and personal property. | Not Started | 2023-07-28 | -254 |  |  | Office of the Chief Administrative Officer | Open - Resolved | The AOC concurs. The Board of Survey process, in accordance with AOC Order 34-45, Personal Property Manual, is conducted by the Supplies, Services and Material Management Division (SSMMD) on lost, damaged or destroyed (LDD) personal property that has been logged into and accounted for in the Maximo inventory control system (ICS). Restitution of LDD personal property logged into and accounted for in Maximo are identified in AOC Order 34-45 under Section 8.13.5 and Appendix D. Additionally Policy Memorandum 752-1, Discipline, lists specific penalties in its Table of Penalties for loss or damage of government property.Mobile devices and other ITD personal property are not logged into or accounted for within the Maximo ICS system; therefore, a Board of Survey is not conducted by SSMMD. Thus, ITD will incorporate a process to address the auditor's recommendation within the Order 8-4 update. | As referenced in the AOC's management response to this recommendation in the EvaluationReport, ITD will be incorporating a process to address the auditor's recommendation within theOrder 8-4 update. As noted above, the updated order is expected to be completed in early 2024,but timing depends on the appointment of a permanent Chief Administrative Officer. | Information Technology Division | Yes | No
FY19 Audit_AOC Multi-Million Dollar Construction Project's Contract Provisions (BPA19 - TO09) | 2021-AUD-012-A | Audit Division | 2022-07-29 | 0 | 0 | 0 | Yes | Recommendation 1 | Concur | We recommend that the Architect of the Capitol (AOC) consider structuring future Guaranteed Maximum Price contracts as 1) fixed-price amounts for general conditions and general requirements and 2) cost reimbursement for subcontracts that are fixed-price amounts between the general contractor and subcontractors, to assist in alleviating the AOC’s administrative burden in properly administering the contract. | Reviewed-In Progress | 2023-07-28 | -254 |  |  | Office of the Chief Engineer | Open - Resolved | Prior to using the Guaranteed Maximum Price contract type on future procurements, we will evaluate best practices and lessons learned and update Contracting Officer guidance for the proper use of this contract type. | See supporting documentation for recommendation 1. | Design & Construction Acquisition Division , Planning & Project Development Division, Project Management Division | Yes | No
FY19 Audit_AOC Multi-Million Dollar Construction Project's Contract Provisions (BPA19 - TO09) | 2021-AUD-012-A | Audit Division | 2022-07-29 | 0 | 0 | 0 | Yes | Recommendation 2 | Concur | We recommend that the Architect of the Capitol (AOC) issue contract modifications for the sampled contracts to include any applicable clauses that the AOC did not include in the contract at the time of award or in any modifications already issued, if the AOC determines that it is feasible to do so. | Reviewed-In Progress | 2023-07-28 | -254 |  |  | Office of the Chief Engineer | Open - Resolved | We concur. The AOC will perform an analysis if it is feasible and or appropriate to perform contract modifications for the clauses in question. |  | Design & Construction Acquisition Division , Planning & Project Development Division, Project Management Division | Yes | No
FY19 Audit_AOC Multi-Million Dollar Construction Project's Contract Provisions (BPA19 - TO09) | 2021-AUD-012-A | Audit Division | 2022-07-29 | 0 | 0 | 0 | Yes | Recommendation 5 | Concur | We recommend that the Architect of the Capitol (AOC) issue contract modifications to remove the inapplicable clauses included in the contract, if the AOC determines that it is beneficial and feasible to do so. | Reviewed-In Progress | 2023-07-28 | -254 |  |  | Office of the Chief Engineer | Open - Resolved | We concur. The AOC will perform an analysis to determine if it is feasible and beneficial to perform contract modifications to remove inapplicable clauses. | See supporting documentation for recommendation 5. | Design & Construction Acquisition Division , Project Management Division | Yes | No
FY19 Audit_AOC Multi-Million Dollar Construction Project's Contract Provisions (BPA19 - TO09) | 2021-AUD-012-A | Audit Division | 2022-07-29 | 0 | 0 | 0 | Yes | Recommendation 6 | Concur | As a part of the Architect of the Capitol (AOC) annual review of active contracts to determine whether any contract modifications are necessary, we recommend that the AOC incorporate a review to identify (1) applicable clauses erroneously omitted during the formulation of the contract, (2) applicable contract clauses issued after contract award, and (3) inapplicable contract clauses. | Reviewed-In Progress | 2023-07-28 | -254 |  |  | Office of the Chief Engineer | Open - Resolved | We concur. We will assess our resources and consider including this recommendation as part of our existing Contract Management Annual Review. | See supporting documentation for recommendation 6 and link below. | Design & Construction Acquisition Division , Project Management Division | Yes | No
FY19 Audit_AOC Multi-Million Dollar Construction Project's Contract Provisions (BPA19 - TO09) | 2021-AUD-012-A | Audit Division | 2022-07-29 | 0 | 0 | 0 | Yes | Recommendation 7 | Concur | We recommend that the Architect of the Capitol (AOC) consider requiring its contractors to carry builder’s risk policies on a project-by-project basis, based on an evaluation of the risks that each project poses to the AOC. | Reviewed-In Progress | 2023-07-28 | -254 |  |  | Office of the Chief Engineer | Open - Resolved | We will consider requiring contractors to carry builder’s risk policies on a project-by-project basis. | See link for supporting documentation for recommendation 7 | Design & Construction Acquisition Division , Project Management Division | Yes | No
AOC’s Construction Potential Change Orders (PCOs) September 2022 | 2022-AUD-012-O | Audit Division | 2023-03-30 | 19675 | 0 | 722083 | Yes | Recommendation 1 | Partially Concur | We recommend the Architect of the Capitol (AOC) perform the following:a. Recover the questioned costs of $6,464 identified within the R-Tunnel Project to the extent legally and administratively possible.b. Review the questioned costs of $68,940 ($75,404 - $6,464) identified within the Cannon House Office Building Renewal ($53,663) and R-Tunnel ($15,277) projects to determine if the costs are allowable in accordance with contract requirements; and as applicable, recover any additional amounts resulting from the application of items like overhead and profits to the unallowable costs.c. Ensure future change orders adhere to the contractual language regarding overhead costs not being allowed as direct costs; and when the AOC determines that overhead costs are allowable as direct costs, document how and why that determination was made. | Reviewed-In Progress | 2024-03-29 | -9 | 2024-05-15 |  | Office of the Chief Engineer, Office of the Chief of Operations | Open - Resolved | We concur with 1a. The AOC will work to recover the questioned costs if it is legally and administratively possible.We partially concur with 1b. The AOC does not concur with 1b as it relates to the Cannon House Office Building Renewal (CHOBr) Project but concur with 1b for the R-Tunnel Project. As stated during the OIG's review of change order documentation and cited on Page 3 of their report, we disagree with the OIG's finding on the CHOBr Project.We concur with lc. We will review existing processes for the AOC's review of contractor submitted potential changes and their respective supporting documentation to ensure compliance with existing AOC policies and procedures and executed contracts. | To close recommendation 1c, theAOC: reviewed 26 PCOs for compliance with existing processes and noted the issues. The issues were sent to the contractor for review and resolution. created aPCO checklist, with tabs verifying calculations and price verification, is now completed, and submitted to the COR and CO with every change order package. The checklist also highlights examples of unallowable costs. revised the Price Negotiation Memorandum form now includes a narrative of merit, justification, discussions, and negotiations from receipt of the proposal to the execution of the final directive. prior to this recommendation in 2022, the process was strengthened to include IGEs for all changes valued at $25,000 or greater. | Design & Construction Acquisition Division , Planning & Project Development Division, Project Management Division, House Office Buildings, Senate Office Buildings | Yes | No
AOC’s Construction Potential Change Orders (PCOs) September 2022 | 2022-AUD-012-O | Audit Division | 2023-03-30 | 19675 | 0 | 722083 | Yes | Recommendation 2 | Partially Concur | We recommend the Architect of the Capitol (AOC) perform the following:a. Review the questioned costs of $167,628 once the AOC determines whether Clark/Christman, A Joint Venture (CCJV) met the incentive fee requirements; if CCJV does not meet the incentive fee requirements and the 100 percent unspent project contingency funds are not awarded, the AOC should recover to the extent legally and administratively possible the AOC’s proportional share of the of the questioned costs.b. Ensure project funds are not used to pay for damages caused by the contractor, even if those funds may be earned by the contractor at a later date. | Reviewed-In Progress | 2024-03-29 | -9 | 2024-05-15 |  | Office of the Chief Engineer | Open - Resolved | Partially concur. Do not concur with 2a; however, concur with 2b. Detailed response included in the final memo. |  | Design & Construction Acquisition Division , Planning & Project Development Division, Project Management Division, House Office Buildings | Yes | No
AOC’s Construction Potential Change Orders (PCOs) September 2022 | 2022-AUD-012-O | Audit Division | 2023-03-30 | 19675 | 0 | 722083 | Yes | Recommendation 4 | Partially Concur | We recommend the Architect of the Capitol (AOC) perform the following:a. Recover the questioned costs of $2,716 identified within the R-Tunnel Project to the extent legally and administratively possible.b. Review the insufficient supported questioned costs of $478,557 ($481,273 - $2,716) identified within the Cannon House Office Building Renewal (CHOBr) ($367,315) and R-Tunnel ($111,242) projects to determine if the costs are supported and allowable; for any of the costs deemed unsupported and/or unallowable, recover the costs to the extent legally and administratively possible; as applicable, recover any additional amounts resulting from the application of items such as overhead and profits to the unallowable costs. | Reviewed-In Progress | 2024-03-29 | -9 | 2024-05-15 |  | Office of the Chief Engineer | Open - Resolved | We concur with 4a and 4b related to the R-Tunnel project.We do not concur with 4b related to the CHOBr project. These are not insufficient supported costs. The total cost of the proposals in question fell within 10 percent of the independent government estimate (IGE). As a best practice the IGE supports the total cost of a change and subcontractor proposal analysis is not required to determine price reasonableness. To complete a full cost analysis and full negotiation for every subcontractor would take considerably more resources (people, time, and money) than are currently in place. If the full scope IGE is within 10 percent of a proposal amount further analysis is not needed. |  | Design & Construction Acquisition Division , Project Management Division, House Office Buildings, Senate Office Buildings | Yes | No
AOC’s Construction Potential Change Orders (PCOs) September 2022 | 2022-AUD-012-O | Audit Division | 2023-03-30 | 19675 | 0 | 722083 | Yes | Recommendation 5 | Concur | We recommend the Architect of the Capitol (AOC) recover the unsupported questioned costs of $6,944 identified within the Cannon House Office Building Renewal ($226) and R-Tunnel ($6,718) projects to the extent legally and administratively possible. | Reviewed-In Progress | 2024-03-29 | -9 | 2024-05-15 |  | Office of the Chief Engineer, Office of the Chief of Operations | Open - Resolved | We concur. The AOC will work to recover the questioned costs if it is legally and administratively possible. |  | Design & Construction Acquisition Division , Project Management Division, House Office Buildings, Senate Office Buildings | Yes | No
AOC’s Construction Potential Change Orders (PCOs) September 2022 | 2022-AUD-012-O | Audit Division | 2023-03-30 | 19675 | 0 | 722083 | Yes | Recommendation 7 | Concur | We recommend the Architect of the Capitol (AOC) comply with the sequence of review and approval for its change orders as prescribed by its policies and procedures and ensure sufficient documentation is maintained. If the AOC deviates from its policies and procedures, the AOC should fully document the reason for the deviation. | Reviewed-In Progress | 2024-03-29 | -9 | 2024-05-15 |  | Office of the Chief Engineer | Open - Resolved | We concur. We will review existing processes for the AOC's review of contractor-submitted potential changes and their respective supporting documentation to ensure compliance with existing AOC policies and procedures. |  | Design & Construction Acquisition Division , Planning & Project Development Division | Yes | No
AOC’s Construction Potential Change Orders (PCOs) September 2022 | 2022-AUD-012-O | Audit Division | 2023-03-30 | 19675 | 0 | 722083 | Yes | Recommendation 8 | Concur | We recommend the Architect of the Capitol (AOC) recover or not award the questioned costs of $3,551 identified within the Exterior Stone & Metal Preservation, Phase III project to the extent legally and administratively possible and ensure the contractor excludes subcontractor profit prior to applying contractual markups. | Reviewed-In Progress | 2024-03-29 | -9 | 2024-05-15 |  | Office of the Chief Engineer | Open - Resolved | We concur. To the extent legally and administratively possible, the AOC will recover the questioned costs. |  | Design & Construction Acquisition Division , Project Management Division, Capitol Building | Yes | No